## Master Checklist
SANKALAN 2026 — LOGISTICS MASTER CHECKLIST
Corporate Communications Committee ¦ PGDM-BM ¦ MDI Gurgaon ¦ Event Date: 20 June 2026
STATUS LEGEND: ✅ Done ¦ 🔄 In Progress ¦ ❌ Not Started ¦ ⚠️ Blocked / Query ¦ PRIORITY: 🔴 Critical 🟠 High 🟡 Medium 🟢 Low
# | Category | Task / Item | Owner | Deadline | Priority | Status | Notes / Vendor Details
VENUE & SETUP
1 | Venue & Setup | Book Auditorium for 20 June (10 AM – 6 PM) | Logistics Head | 25-May | 🔴 Critical | ❌ Not Started | Confirm with admin; Inauguration + CaseQuest + Panel all in Auditorium
2 | Venue & Setup | Book MDP Hall for Cultural Night (7 PM onwards) + Takshille for student get-together | Logistics Head | 25-May | 🔴 Critical | ❌ Not Started | MDP Hall = formal cultural space; Takshille exterior = informal dinner setting with lights ¦ Confirm both with admin by May 25
3 | Venue & Setup | Book Syndicate Room (backup / prep room for panelists) | Logistics Head | 27-May | 🟠 High | ❌ Not Started | Panelist holding area 1:30–3 PM; needs sofa, table, water
4 | Venue & Setup | Venue walk-through with full logistics team | Logistics Head | 05-Jun | 🟠 High | ❌ Not Started | Map: registration desk, stage, seating, catering stations, photo wall, CaseQuest area
5 | Venue & Setup | Arrange sofa & table for panelist green room | Logistics Head | 10-Jun | 🟡 Medium | ❌ Not Started | Coordinate with estate/admin; confirm 4–5 seater sofa
6 | Venue & Setup | Stage layout & seating plan (auditorium) | Logistics Head | 10-Jun | 🟠 High | ❌ Not Started | 7 panelists + 1 moderator on stage; reserve front rows for guests/faculty
7 | Venue & Setup | Keep front row(s) empty/reserved for dignitaries | Volunteer Lead | 20-Jun | 🟡 Medium | ❌ Not Started | Previous year note: keep 1st lane empty for chief guest & dean
8 | Venue & Setup | Morning cleaning & venue setup check (8 AM) | Logistics Head | 20-Jun | 🔴 Critical | ❌ Not Started | Arrive 2 hrs before event; verify décor, AV, seating all in place
DÉCOR & PROPS
9 | Décor & Props | Flower decoration — stage & venue (bouquets + plants) | Décor Owner | 10-Jun | 🟠 High | ❌ Not Started | Budget: ₹15,000 ¦ Get 2-3 quotes; plants for gifting also included
10 | Décor & Props | Standee design & print | Content Team | 05-Jun | 🟠 High | ❌ Not Started | Budget within ₹20,000 props total ¦ Need design file from content team by May 30
11 | Décor & Props | Banner(s) — Auditorium + MDP Hall | Content Team | 05-Jun | 🟠 High | ❌ Not Started | Confirm sizes with venue; include event theme 'Zero-Based Strategy'
12 | Décor & Props | Selfie board / Memory board | Content Team | 08-Jun | 🟡 Medium | ❌ Not Started | Budget within ₹20,000 props total ¦ Place near auditorium entrance
13 | Décor & Props | Evening lights — Takshille Dining Hall exterior (cultural night setup) | Décor Owner | 15-Jun | 🟠 High | ❌ Not Started | 'Lagwaana' = fit/install lights outside Takshille for get-together atmosphere ¦ Contact S.D. Charan (State Office) for electrical points
14 | Décor & Props | Red carpet — lay outside Auditorium entrance for panelist arrival | Logistics Head | 12-Jun | 🟡 Medium | ❌ Not Started | Previous year reference: red carpet outside auditorium; coordinate with estate/admin for placement by 9 AM
PHOTOGRAPHY & AV
15 | Photography & AV | Hire photographer + videographer (full day) | Logistics Head | 30-May | 🔴 Critical | ❌ Not Started | Budget: ₹18,000 ¦ 10 AM–10 PM; deliverables: reels + edited stills within 48 hrs
16 | Photography & AV | AV / mic setup — contact S.D. Charan (State Office) for power/light points | Logistics Head | 05-Jun | 🔴 Critical | ❌ Not Started | S.D. Charan = MDI estate/state office staff for electrical connections ¦ Lapel mics for 7 panelists + moderator; handheld for Q&A
17 | Photography & AV | IT arrangements — laptop, projector, clicker | IT/Volunteer | 10-Jun | 🟠 High | ❌ Not Started | CaseQuest teams need projector; backup laptop on standby
18 | Photography & AV | Computer operator / tech volunteer on event day | IT/Volunteer | 20-Jun | 🟠 High | ❌ Not Started | Dedicated tech person for slides, live polls, AV; should be present from 8 AM
19 | Photography & AV | Musical setup for cultural night (DJ / live music) | Logistics Head | 05-Jun | 🟠 High | ❌ Not Started | Budget within ₹75,000 dinner total ¦ Clarify: DJ or live act? Affects budget split
20 | Photography & AV | Lighting — Auditorium + MDP Hall | Décor Owner | 10-Jun | 🟡 Medium | ❌ Not Started | Stage lighting for panel; festive lighting for cultural night
F&B
21 | F&B | Lock F&B vendor (full day) | F&B Owner | 30-May | 🔴 Critical | ❌ Not Started | Budget: ₹30,000 lunch+hi-tea + ₹75,000 dinner ¦ Get 2-3 quotes; confirm GST
22 | F&B | Lunch — 12:30 PM ¦ Students → Takshille Dining Hall (57 students via Mess) | F&B Owner | 15-Jun | 🔴 Critical | ❌ Not Started | Coordinate with Mess; separate from guest lunch. Confirm student headcount.
23 | F&B | Hi-Tea 2 — Panelist Hi-Tea (4:30 PM) ¦ CaseQuest winners + panelists | F&B Owner | 15-Jun | 🟠 High | ❌ Not Started | Winners earn 1-on-1 hi-tea with panelist; confirm exact count after CaseQuest judging
24 | F&B | Hi-Tea 1 — Post-Inauguration (10:30 AM) ¦ Light refreshments, Auditorium foyer | F&B Owner | 15-Jun | 🟡 Medium | ❌ Not Started | Separate from panelist hi-tea; light snacks/tea for students + guests after inauguration ceremony
25 | F&B | Get-together Dinner — 7 PM onwards (65-70 pax) | F&B Owner | 15-Jun | 🔴 Critical | ❌ Not Started | Budget: ₹75,000 incl. décor + music; confirm 3-4 panelists staying back
26 | F&B | Water bottles + mints on panelist table (event day) | Volunteer Lead | 20-Jun | 🟡 Medium | ❌ Not Started | 6 water bottles on stage table; replenish during breaks
27 | F&B | Fix lunch rate with Jha ji — NMP Hall (MDP Dining) for guests & faculty | Logistics Head | 12-Jun | 🟢 Low | ⚠️ Blocked | NMP = MDP Dining Hall ¦ Jha ji is MDI staff contact ¦ Confirm per-head rate for ~17 guests+faculty; negotiate before June 1
PANELIST MGMT
28 | Panelist Mgmt | Create Panelist Info Sheet (all 7 + moderator) | Logistics Head | 27-May | 🔴 Critical | ❌ Not Started | Fields: name, designation, contact, pickup point, dietary pref, staying for dinner Y/N
29 | Panelist Mgmt | Domestic conveyance — confirm pickup/drop for each panelist | Conveyance Owner | 10-Jun | 🔴 Critical | ❌ Not Started | Budget: ₹25,000 (~8 cabs); book reliable cab vendor; map airport/station vs local
30 | Panelist Mgmt | Flight ticket — confirm if any panelist needs Bombay–Delhi booking | Logistics Head | 01-Jun | 🟠 High | ❌ Not Started | Previous year had Mumbai-Delhi flight; check with each panelist; handle reimbursement
31 | Panelist Mgmt | Assign dedicated volunteer per panelist (on event day) | Volunteer Lead | 15-Jun | 🟠 High | ❌ Not Started | Volunteer picks up panelist from gate, escorts to green room, stage, hi-tea, exit
32 | Panelist Mgmt | Confirm 3-4 panelists staying back for cultural night | Logistics Head | 12-Jun | 🟡 Medium | ❌ Not Started | Needed for dinner headcount; brief panelists on informal interaction format
33 | Panelist Mgmt | Name plates for panelists on stage | Volunteer Lead | 18-Jun | 🟡 Medium | ❌ Not Started | Print tent cards with name + designation; font size visible from audience
GIFTS & FELICITATION
34 | Gifts & Felicitation | Order corporate gifts — 10 sets (laptop bag + books + MDI logo items) | Gifts Owner | 01-Jun | 🔴 Critical | ❌ Not Started | Budget: ₹38,000 ¦ ⚠️ LONGEST LEAD TIME — 10-14 days for MDI embossing; order by June 1
35 | Gifts & Felicitation | Bouquets for Chief Guest, Dean, Chairpersons | Gifts Owner | 19-Jun | 🟠 High | ❌ Not Started | Within ₹15,000 décor budget; confirm count of dignitaries receiving bouquets
36 | Gifts & Felicitation | Momento / memento for special guests | Gifts Owner | 10-Jun | 🟡 Medium | ❌ Not Started | Previous year note: confirm if separate memento or part of gift set
37 | Gifts & Felicitation | Confirm gift list — who receives what (protocol) | Logistics Head | 05-Jun | 🟠 High | ❌ Not Started | Chief Guest, 7 panelists, Dean, Chairpersons — total ~10; confirm with secretary
CASEQUEST SETUP
38 | CaseQuest Setup | Coordinate with academic team — get case problem content | Logistics Head | 27-May | 🔴 Critical | ❌ Not Started | Case to be released 48-72 hrs before event (June 17-18); need content by May 30 to print
39 | CaseQuest Setup | Print case packets for all participating teams | CaseQuest Owner | 15-Jun | 🟠 High | ❌ Not Started | Budget: ₹7,500 total ¦ Packet includes: case problem, evaluation sheet, instructions
40 | CaseQuest Setup | Evaluation sheets for faculty judges (internal round) | CaseQuest Owner | 15-Jun | 🟠 High | ❌ Not Started | Criteria: analytical rigour, creativity, feasibility, presentation quality
41 | CaseQuest Setup | Certificates of excellence — design + print | Content Team | 12-Jun | 🟡 Medium | ❌ Not Started | For winning team(s) + top 3 finalists; get design from content team
42 | CaseQuest Setup | Prize envelopes — cash prizes ready | Logistics Head | 18-Jun | 🔴 Critical | ❌ Not Started | Budget: ₹25,000 for prizes; confirm denomination breakdown; keep in sealed envelopes
43 | CaseQuest Setup | Setup presentation area in Auditorium for CaseQuest | Logistics Head | 20-Jun | 🟠 High | ❌ Not Started | Projector + laptop + clicker for top-3 teams; timer visible to presenter
44 | CaseQuest Setup | Plastic folders (~20) + stationery for student teams | Logistics Head | 15-Jun | 🟢 Low | ❌ Not Started | Previous year: 69 IDs with 10 pencils; adapt for 57 students; include notepads
INVITATIONS & COMMS
45 | Invitations & Comms | Send formal invitation cards to all panelists | Comms Team | 25-May | 🔴 Critical | ❌ Not Started | Coordinate with Manasi (Secretary); confirm digital + physical invite format
46 | Invitations & Comms | Invitation to Dean, Chairpersons, Faculty | Comms Team | 25-May | 🔴 Critical | ❌ Not Started | Coordinate with Director's office / diary management
47 | Invitations & Comms | Alumni outreach — personal calls for cultural night | Comms Team | 01-Jun | 🟠 High | ❌ Not Started | Previous year: personal call to NRC alums; confirm attire guidance too
48 | Invitations & Comms | Director's office — diary entry & formal note | Comms Team | 27-May | 🟠 High | ❌ Not Started | Block Dean + Director calendar for June 20; send agenda
49 | Invitations & Comms | LinkedIn event post + social media promotion | Content Team | 01-Jun | 🟡 Medium | ❌ Not Started | Amplify via MDI LinkedIn page; student/panelist tags; pre-event content
VOLUNTEERS
50 | Volunteers | Recruit 6-8 volunteers (logistics, ushering, registration) | Volunteer Lead | 27-May | 🟠 High | ❌ Not Started | Roles: gate reception, panelist escort, F&B, AV assist, registration desk, CaseQuest
51 | Volunteers | Volunteer briefing + role assignment | Volunteer Lead | 15-Jun | 🔴 Critical | ❌ Not Started | Share day-of runsheet; each volunteer has ONE owner domain, not multiple
52 | Volunteers | Registration desk setup (student + guest check-in) | Volunteer Lead | 20-Jun | 🟡 Medium | ❌ Not Started | Printed name tags + attendance sheet; separate queue for guests vs students
53 | Volunteers | Host/Emcee confirmed + briefed | Comms Team | 10-Jun | 🟠 High | ❌ Not Started | Prepare full event script with timings; include vote of thanks, panelist intros
54 | Volunteers | Vote of thanks — drafted and assigned | Comms Team | 12-Jun | 🟡 Medium | ❌ Not Started | Usually Secretary or student leader; include acknowledgement of each panelist
DAY-OF RUNSHEET
55 | Day-of Runsheet | Prepare master day-of runsheet with all timings | Logistics Head | 14-Jun | 🔴 Critical | ❌ Not Started | Include: slot timings, responsible person, vendor contact, contingency for each item
56 | Day-of Runsheet | Brochure + pen + bottle + notepad on each student seat | Volunteer Lead | 20-Jun | 🟡 Medium | ❌ Not Started | 57 students; confirm brochure design with content team by June 10
57 | Day-of Runsheet | Group photo — schedule immediately after inauguration | Volunteer Lead | 20-Jun | 🟢 Low | ❌ Not Started | Previous year flow: High-tea 10:30 → Group photo → MOP lunch 12:00
58 | Day-of Runsheet | Dean speech + Chairperson speech — scripts confirmed | Comms Team | 15-Jun | 🟡 Medium | ❌ Not Started | Coordinate with respective offices; share event context + panelist bios
59 | Day-of Runsheet | Moderator briefed — questions + flow for panel discussion | Comms Team | 10-Jun | 🟠 High | ❌ Not Started | Share panelist bios + discussion theme; pre-event call with moderator
60 | Day-of Runsheet | Post-event: collect all bills, return unutilized funds | Logistics Head | 22-Jun | 🔴 Critical | ❌ Not Started | Per proposal: Manasi Sharma takes responsibility; submit self-attested bills
MDI STAFF & INTERNAL COORDINATION
61 | MDI Staff Coord. | Book Parthenon rooms — 2 rooms for June 19, 20, 21 (3 nights) | Logistics Head | 23-May | 🔴 Critical | ❌ Not Started | URGENT — book immediately; 2 rooms for outstation panelists / Chief Guest stay; confirm check-in June 19 evening
62 | MDI Staff Coord. | Volunteer on duty — Friday June 19 (5 PM) for Parthenon guest check-in | Volunteer Lead | 15-Jun | 🔴 Critical | ❌ Not Started | Volunteer must be present at Parthenon from ~5 PM June 19; assist guests with room check-in, directions, any needs
63 | MDI Staff Coord. | Coordinate with S.D. Charan (State Office) — electrical/light points for AV & décor | Logistics Head | 01-Jun | 🟠 High | ❌ Not Started | S.D. Charan = MDI state office / estate staff ¦ Needed for: stage lights, Takshille exterior lights, mic power points in Auditorium
64 | MDI Staff Coord. | Fix lunch rate with Jha ji — NMP / MDP Dining Hall (guest & faculty lunch) | Logistics Head | 27-May | 🔴 Critical | ❌ Not Started | Jha ji = MDI dining staff ¦ NMP Hall = MDP Dining Hall ¦ Fix per-head rate for ~17 pax (10-12 guests + 5 faculty); get written confirmation
65 | MDI Staff Coord. | Takshille Dining Hall — confirm student lunch arrangement (57 students via Mess) | Logistics Head | 27-May | 🟠 High | ❌ Not Started | Students eat at Takshille (regular mess); coordinate with mess in-charge to ensure capacity & timing aligns with 12:30 PM schedule
66 | MDI Staff Coord. | Evening lights — Takshille exterior (cultural night) via S.D. Charan | Décor Owner | 10-Jun | 🟠 High | ❌ Not Started | 'Lights lagwaana' outside Takshille dining hall for get-together atmosphere; S.D. Charan to provide power connection points; décor vendor to supply lights

## Budget Tracker
SANKALAN 2026 — BUDGET TRACKER
Logistics Head Budget Reference ¦ All figures in INR
S.No. | Category | Budget (INR) | Quoted (INR) | Advance Paid | Balance / Notes
1 | Flower Decoration (venue, bouquets, gifting plants) | 15000
2 | Photography & Videography (full day) | 18000
3 | Promotion Props (Standee, Banner, Selfie Board, Memory Board) | 20000
4 | CaseQuest Prize Money | 25000
5 | Lunch & Hi-Tea (guests+faculty at NMP/MDP Hall via Jha ji + 2 hi-tea sessions) | 30000 |  |  | Split: guest lunch at NMP Hall (Jha ji rate) + students via Takshille Mess; 2 hi-teas: post-inauguration + panelist 4:30 PM
6 | Felicitation Gifts — 10 sets (laptop bag, books, MDI merch) | 38000
7 | Get-Together & Dinner (décor, DJ/music, lighting — 65-70 pax) | 75000
8 | Domestic Conveyance (panelist cabs, airport transfers) | 25000
9 | CaseQuest Competition Setup (printing, certs, eval materials) | 7500
| TOTAL SANCTIONED BUDGET | 253500 | 0 | 0 | ← 80% advance; 20% post-event on bills
| Budget vs Quoted Variance | 253500 | Positive = under budget
ADVANCE TRANSFER: Manasi Sharma ¦ ICICI Bank ¦ A/C: 192901503858 ¦ IFSC: ICICI0001929 ¦ Request 80% advance before event

## Panelist Tracker
SANKALAN 2026 — PANELIST LOGISTICS TRACKER
Complete one row per panelist ¦ Update status as confirmations come in
# | Name | Designation & Company | Contact No. | Pickup Point | Cab Booked? | Dietary Pref. | Staying for Dinner? | Volunteer Assigned | Parthenon Room?
1 | Gopal C Sikder | Sr. EVP & Project Director, Reliance Industries Ltd
2 | Rushati Ghosh | GM Marketing Head, Business Octane Solutions Pvt Ltd
3 | Neha Gupta | MD & Partner, Boston Consulting Group (BCG)
4 | Naveen Gulati | Group CTO, Modi Enterprises
5 | Somnath Das | VP — Supply Chain, Flipkart
6 | Rakhi Aswal | CFO — Saxo Group India
7 | Rajeev Singh | VP, Genpact — Manufacturing Finance & Transformation
8 | Moderator TBD | To be confirmed